## Sheet1
OPTION #5 - LEAVE EXISTING STOCKPILES AND HAUL REMAINING EXCAVATION OFF PROPERTY TO DEL RIO AND ROADWAYS
|  | 30% GMP |  |  |  | Suggested Costing
| Description | Quantity | Unit | Unit Price | Extension | Quantity | Unit | Unit Price | Extension
1 | Mobilization | 1 | Lump Sum | 2900000 | 2900000 | 1 | Lump Sum | 2900000 | 2900000
2 | Erosion Control (Hay) | 125 | Each | 70 | 8750 | 125 | Each | 70 | 8750
3 | Erosion Control (Silt Fence) | 18880 | Linear Foot | 2.5 | 47200 | 18880 | Linear Foot | 2.5 | 47200
4 | Limited Excavation - Pond 3 | 184493 | Cubic Yard | 8.75 | 1614313.75 | 184493 | Cubic Yard | 8.75 | 1614313.75
5 | Limited Excavation - Pond 4 | 126294 | Cubic Yard | 8.75 | 1105072.5 | 126294 | Cubic Yard | 8.75 | 1105072.5
6 | CMAR Preconstruction Services | 1 | Lump Sum | 20025 | 20025 | 1 | Lump Sum | 20000 | 20000
7 | Limited Excavation - Pond 2 (Short Haul) | 689213 | Cubic Yard | 9.5 | 6547523.5 | 750000 | Cubic Yard | 9.5 | 7125000
8 | Limited Excavation - Pond 2 (Long Haul Off Road) | 1012269 | Cubic Yard | 10.5 | 10628824.5 | 1000000 | Cubic Yard | 10.5 | 10500000
9 | Limited Excavation - Pond 2 (Long Haul On Road) | 1000000 | Cubic Yard | 13.5 | 13500000 | 312000 | Cubic Yard | 13.5 | 4212000
10 | Clearing & Grubbing | 1 | Lump Sum | 188000 | 188000 | 40 | Acre | 4000 | 160000
11 | Removal of Structures and Obstructions | 1 | Lump Sum | 35000 | 35000 | 1 | Lump Sum | 20000 | 20000
12 | Site Embankment of Raised Roadway and Ditch Excavation | 1 | Lump Sum | 250000 | 250000 | 12000 | Linear Foot | 5 | 60000
13 | Geotextile Fabric | 1000 | Square Yard | 3.5 | 3500 | 1000 | Square Yard | 3.5 | 3500
14 | Storm Drain Pipe - 24" RCP | 140 | Linear Foot | 105 | 14700 | 140 | Linear Foot | 105 | 14700
15 | Storm Drain Pipe - 48" RCP | 512 | Linear Foot | 205 | 104960 | 512 | Linear Foot | 205 | 104960
16 | Incidental Concrete Paving (4" Thick) | 150 | Square Yard | 80 | 12000 | 150 | Square Yard | 80 | 12000
17 | Flowable Fill (Type 1) | 100 | Cubic Yard | 200 | 20000 | 100 | Cubic Yard | 200 | 20000
18 | Riprap (Class 10 & 1') | 200 | Square Yard | 75 | 15000 | 200 | Square Yard | 75 | 15000
19 | Temporary Signs and Barricades | 1 | Lump Sum | 36500 | 36500 | 1 | Lump Sum | 25000 | 25000
20 | Erosion Control System (Slope Protection)(Type C) | 150000 | Square Yard | 2.3 | 345000 | 150000 | Square Yard | 2.3 | 345000
21 | Port-O-Let | 1 | Each | 7500 | 7500 | 1 | Each | 7500 | 7500
22 | Project Site Office Building | 1 | Each | 15000 | 15000 | 1 | Each | 15000 | 15000
23 | Hydroseeding | 35 | Acre | 750 | 26250 | 35 | Acre | 750 | 26250
24 | Construction Layout | 1 | Lump Sum | 47500 | 47500 | 1 | Lump Sum | 47500 | 47500
25 | Construction Photographs and Video | 1 | Lump Sum | 9500 | 9500 | 1 | Lump Sum | 9500 | 9500
26 | Outfall Structure (5'x5') | 2 | Each | 20000 | 40000 | 2 | Each | 18000 | 36000
27 | Dry Hydrant | 3 | Each | 4500 | 13500 | 3 | Each | 4500 | 13500
28 | Flap Gate (24" Diameter) | 2 | Each | 9500 | 19000 | 2 | Each | 9500 | 19000
29 | Flap Gate (48" Diameter) | 6 | Each | 17500 | 105000 | 6 | Each | 17500 | 105000
30 | Earthen Channel (Temporary) | 9700 | Cubic Yard | 9.5 | 92150 | 9700 | Cubic Yard | 8 | 77600
31 | Landscape Allowance | 1 | Lump Sum | 0 | 0 | 1 | Lump Sum | 75000 | 75000
32 | Site Grading Allowance | 1 | Lump Sum | 150000 | 150000 | 1 | Lump Sum | 150000 | 150000
33 | Project Sign | 1 | Each | 8000 | 8000 | 2 | Each | 8000 | 16000
34 | Temporary/Permanent Fence | 1 | Lump Sum | 160000 | 160000 | 2000 | Linear Foot | 15 | 30000
35 | Permanent Fence (Type 1) | 3500 | Linear Foot |  | 0 | 0 | Linear Foot | 18 | 0
36 | Permanent Fence (Type 2) | 8100 | Linear Foot |  | 0 | 0 | Linear Foot | 20 | 0
37 | All Weather Road (12' wide x 4" thick) | 5000 | Linear Foot |  | 0 | 2500 | Linear Foot | 75 | 187500
38 | Access Area Lighting | 1 | Lump Sum |  | 0 | 1 | Lump Sum | 25000 | 25000
39 | Entrance Gate (Double 8', 16' total) |  |  |  |  | 3 | Each | 8000 | 24000
40 | Interior Piping |  |  |  |  | 500 | Linear Foot | 300 | 150000
42 | Contingencies |  |  |  |  | 1 | Lump Sum | 280000 | 280000
[5 empty] | 38089769.25 |  |  |  | 29606846.25
CONS
1) | Option allows for additional excavation of approximately 1,312,000 cu. yds. to be hauled off property to Del Rio and roadways. This provides for the moderate expansion of Pond 2.
2) | Hauling off remainder of excavation would require over 34,000 one way trips (loaded) and 34,000 trips unloaded through Rue Fosse, Homewood and Riverwoods. Would require 24/7 operation.
3) | Would require a 5 year agreement with Rigid to sell stockpiled dirt to partially pacify residents.
4) | Estimated 3 Million costs in road repairs
[6 empty] | Time of Completion (June 30th) |  | % Pond 2 Functional | Residential Sensitivity
| PROS |  |  |  |  | YES |  | 82% Pond 2 | Medium
1) | Would leave the property "as currently is" with regard to ground elevations. |  |  |  |  | YES |  | 28% CIDC | Medium
2) | Less objectional to residents except for the hauling of the material out via the roadway.
3) | Would allow for higher expansion of Pond 2 in Phase II albeit at a higher cost per cubic yard.
4) | Would not eliminate MOST issues with current pipelines or electrical lines
5) | Large portion of remaining excavation would be hauled overland to local land and only partial roadway traffic required.
6) | Option could be to remove all roadway transport and use left over funds of GMP to excavate at Duhon Road.
Allows for an additional 1,312,000 yards to be excavated at Homewood and excavation at Duhon Road if desired.